Instructions to Mr. Ahendera / Josephine / Ikobe
Final Schedule (June 25 – August 11, 2026)
No school should expect donations EXCEPT Nile Rd which will  get Tablets / chromebooks for implementation of the Digital Register
in
Term 3, 2026
















	SN
	Dates
	County
	Incharge
	To Do

	1
	June 25 & 26
	Nairobi
	Goldin, Daniel, Josephine
	MoE, TSC, Kurauka, KICD &Thika

	2
	June 29 – July 5
	Ngoleni Sec Sch , Machakos, Makueni, Kitui
	Margaret Mutie, 
Ben Masika - to make presentation on July 15 in order to complete his training
	Differentiated Instructions for form 4.
Admit atleast 200 schools to KISWATE

	3
	July 6 - 12
	Migori ,
Elgeyo Marakwet,
TransNzoia, Kakamega
	Dr. Onunga  / Sagege
Chemitei
	KISWATE National Transmission Center, Iam_Marwa & Thimlich Ohimga
Recruit 200 schools

	4
	July 13 -19
	Kisii, Homabay, Narok
	Pastor George Agola
	Kisii High School
Recruit 200 schools

	5
	July 20 -26
	Busia, Siaya, Kisumu ,  & Vihiga
	Yuya, Ndolo, Nyajuoga 
	Burumba, Samia & St, Thomas Nduru
Admit atleast 300 schools to Kiswate

	6
	July 27 – Aug 2
	Nairobi, Kiambu & Kajiado
	Ikobe, Ahendera, Gulundu & Odalo
	Admit atleast 400 schools to KISWATE

	7
	Friday July 31, 2026
	KDA is launched at Nile Road Special Sec Sch and KDADTR goes live in all participating schools (Ombwayo, Patrick, Nyangaresi, Mary, James, Mitchell, Amakobe, Moraa, Atyanga and Kaunda). Team leaders -Ahendera /Ikobe /Josephine.All SCDE (MoE / TSC) in the neighborhood to be invited
All schools that benefited from the tour to be represented,Global Peace Foundation to invite CS MoE.Journalists to be invited,

	8
	August 3 & 4, 2026

	Ugenya
	Meet all principals from Ugenya through SCDE (TSC) Ben Orwasa (Yuya, Daniel,  Ahendera & Josephine) physical meeting.No online meeting.


	9
	August 10 &11
	Nairobi
	Goldin, Daniel, Josephine
	MoE, TSC, Kurauka, KICD and Thika










The KISWATE Coordinators to ensure that the principals in each category provide a meal for my team of 5 -12  people and fuel for my  car, 

Requirements for admission to KISWATE Digital Academy
1. Letter of authority to digitize the school from the School Board of Management (BOM)
2. List of teachers and their contacts for training to become Digital Educators
3. Name of the team leader for teachers to be trained
4. Training of teachers  ( December 2026 – April 2027) for 3rd Cohort

Tentative Pilot Dates for KDADTR – Term 1, 2027 and Term 2, 2027
(We are still waiting for authorization from the MoE)
