Instructions to Mr. Ahendera / Josephine / Ikobe

Final Schedule (June 25 – August 11, 2026)

No school should expect donations EXCEPT Nile Rd which will  get Tablets / chromebooks for implementation of the Digital Register

in

Term 3, 2026

| SN | Dates | County | Incharge | To Do |
| --- | --- | --- | --- | --- |
| 1 | June 25 & 26 | Nairobi | Goldin, Daniel, Josephine | MoE, TSC, Kurauka, KICD &Thika |
| 2 | June 29 – July 5 | Ngoleni Sec Sch , Machakos, Makueni, Kitui | Margaret Mutie, Ben Masika - to make presentation on July 15 in order to complete his training | Differentiated Instructions for form 4. Admit atleast 200 schools to KISWATE |
| 3 | July 6 - 12 | Migori , Elgeyo Marakwet, TransNzoia, Kakamega | Dr. Onunga / Sagege Chemitei | KISWATE National Transmission Center, Iam_Marwa & Thimlich Ohimga Recruit 200 schools |
| 4 | July 13 -19 | Kisii, Homabay, Narok | Pastor George Agola | Kisii High School Recruit 200 schools |
| 5 | July 20 -26 | Busia, Siaya, Kisumu , & Vihiga | Yuya, Ndolo, Nyajuoga | Burumba, Samia & St, Thomas Nduru Admit atleast 300 schools to Kiswate |
| 6 | July 27 – Aug 2 | Nairobi, Kiambu & Kajiado | Ikobe, Ahendera, Gulundu & Odalo | Admit atleast 400 schools to KISWATE |
| 7 | Friday July 31, 2026 | KDA is launched at Nile Road Special Sec Sch and KDADTR goes live in all participating schools (Ombwayo, Patrick, Nyangaresi, Mary, James, Mitchell, Amakobe, Moraa, Atyanga and Kaunda). Team leaders -Ahendera /Ikobe /Josephine.All SCDE (MoE / TSC) in the neighborhood to be invited All schools that benefited from the tour to be represented,Global Peace Foundation to invite CS MoE.Journalists to be invited, |  |  |
| 8 | August 3 & 4, 2026 | Ugenya | Meet all principals from Ugenya through SCDE (TSC) Ben Orwasa (Yuya, Daniel, Ahendera & Josephine) physical meeting.No online meeting. |  |
| 9 | August 10 &11 | Nairobi | Goldin, Daniel, Josephine | MoE, TSC, Kurauka, KICD and Thika |

The KISWATE Coordinators to ensure that the principals in each category provide a meal for my team of 5 -12  people and fuel for my  car,

Requirements for admission to KISWATE Digital Academy

- Letter of authority to digitize the school from the School Board of Management (BOM)

- List of teachers and their contacts for training to become Digital Educators

- Name of the team leader for teachers to be trained

- Training of teachers  ( December 2026 – April 2027) for 3rd Cohort

Tentative Pilot Dates for KDADTR – Term 1, 2027 and Term 2, 2027

(We are still waiting for authorization from the MoE)